AERONAUTICAL TELECOMMUNICATIONS NETWORK PANEL(ATNP)

WG1 – Systems planning and concept working group

5-6 October 1998

Bordeaux, France

WG1 Deliverables and Schedule for ATNP/3

(Presented by P. Hennig)

Summary

This Working Paper contains the list of Deliverables which was approved by WG1 at the WG1/9 meeting in Langen. The list is derived from the WG1 Work Program approved at ATNP/2, along with the corresponding delivery dates to ensure completion of the program by ATNP/3.

1.	Introduction

Working Group 1 of ATNP was given a series of work items by ATNP/2 to be completed by ATNP/3.

2.	Discussion

The table below outlines the specific tasks and deliverables for the WG1 work program

| Work Program Item | WG1 Activity | Target Dates |  | Affected Groups |  | Status after WG1/12 |
| --- | --- | --- | --- | --- | --- | --- |
| A Review operational requirements of ICAO bodies (e.g. ADSP, Review of the General Concept of Separation Panel/RGCSP, regional planning and implementation groups, etc.), and determine those to be addressed in revisions to existing draft ATN SARPs (for finalization at ATNP/3); (NB: Ensure that the Security and System Management areas are also included) (NB: Organizations -e.g., IATA- submit requirements directly to ATN Panel) | (1): Definition of Package-2 applications (2): End date cutoff for ADSP |  | Applications - JUN 97 High Level Requirements - OCT 97; Tasking to WG2/3 - OCT 97 JWG/9 communiqué states NO “NEW APPLICATION SARPS FOR ATNP/3” IATA WP12-07+ by Bordeaux Eurocontrol to determine any ODIAC requirements by Bordeaux |  | ADSP | ADSP closed with communiqué approved by JWG/9; other requirements ongoing |
| B & C Develop a security strategy for the ATN including a plan for the administration of the ATN security features; Develop system level SARPs and guidance material for ATN security mechanisms; | Strategy, SARPs & Guidance Material |  | Strategy – JUL 97 Proposed WG2/3 Work Items - JUL 97 Draft 1 SARPs & GM - OCT 97, Final SARPs – MAY 99 Final GM – SEP 99 WG2 initial draft SV5 OCT 98 final JUN 99 |  | WG 2 and 3 | open |
| D & E Develop a system management strategy for the ATN including a plan for the administration of the ATN system management features; Develop system level SARPs and guidance material for ATN system management; | Strategy, SARPs & Guidance Material |  | Strategy - JUL 97 Proposed WG2/3 Work Items - OCT 97 Draft 1 SARPs & GM - FEB 98, Final SARPs - MAY 99 Final GM - SEP 99 |  | WG 2 and 3 JSG | open |
| F Assess the extensibility of the ATN communications services, system management provisions and security provisions; Develop ATN SARPs changes, as needed, to ensure the ATN is extensible to support the long term requirements and configurations; | Report |  | WG1 Rapporteur interim draft report JAN 99; final Report - SEP 99 |  | CCB | open |
| G Ensure backwards compatibility of SARPs enhancements with existing ATN SARPs; (NB: See Terms of Reference for SG1 for definition of this concept) | Definition, methodology and sunset clauses |  | Definition - MAY 97 Methodology - JUL 97 WG1 Rapporteur interim draft report JAN 99; final Report - SEP 99 |  | ADSP WG 2 and 3 | open |
| H & N Develop guidance on safety objectives, (Include consideration of Non-Nominal cases [WG1/11]); Develop end-to-end ATN performance requirements consistent with operating concept; | Guidance Material - SV1, ICAO Manual |  | Initial Guidance Material JAN 99 |  | SC189 WG53 ADSP (RCP) | open |
| I Monitor AFTN and CIDIN developments and develop new procedures for aeronautical fixed services in Annex 10, Volume II, to include those procedures needed to address AMHS as well as AFTN; | SARPs and Guidance Material (CAMAL Part II) |  | Ref: WG1/11 Flimsy 4 CAMAL Part II Draft 1 - FEB 98 |  | WG3 SG1 | open |
| J Review and monitor the regional ATN developments and implementation; Update the Comprehensive ATN Manual (CAMAL), as necessary, to address issues including the transition from existing air-ground data link services based on ACARS/FANS-1 to ATN based services; This is to be facilitated through coordination with ICAO operational panels and regional planning and implementation groups. Coordinate with Working Group 2, Working Group 3 and the Configuration Control Board (CCB) as necessary to resolve transition issues; | CAMAL II |  | PIG1 draft 1 - JUL 97 PIG1- final - OCT 97 CAMAL II draft 1 - FEB 98 CAMAL II final - SEP 99 |  | IATA ADSP RGCSP RPGs | open |
| K Identify potential institutional issues, and monitor development of solutions to those that can be addressed by the ATNP; | Update Institutional Issues document; e.g., how to eliminate or mitigate |  | No new institutional issues since ATNP/2 |  | ICAO | closed |
| L Progress the material presented to ATNP/2 on the naming and addressing framework into guidance material; | Guidance Material |  | Draft 1 - OCT 97 Final CAMAL I |  | WG2 | closed |
| M Develop a document defining the overall ATN operating concept consistent with the operational requirement received from ICAO operational panels and regional planning, implementation and coordinating groups; and (NB: This deals only with the ATN Internet operating philosophy) | Guidance Material |  | Table of Contents - JUL 97 Draft 1 - OCT 97 Final - JUN 98 CAMAL I |  |  | closed |
| O Complete the guidance material associated with the initial ATN SARPs (Sub-Volume I). | Package 1 Guidance Material |  | GM - OCT 97 Update to GM - SEP 98 Final CAMAL I |  |  | closed |

TASKING	SG1:    G, H, J, L, M, N, O	SG2:    B, C	JSG/SG3:    D, E

WG1:	 A, F, K		RAPPORTEUR:    I